## Gantt Chart
Marketplace Gannt
Task | Start (Week) | Duration (Weeks) | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
Project Initiation & Planning | 1 | 2 | bar: W1 to W2
Requirements Analysis | 2 | 2 | bar: W2 to W3
Architecture Design | 3 | 3 | bar: W3 to W5
Backend Development | 5 | 4 | bar: W5 to W8
Frontend Development | 6 | 4 | bar: W6 to W9
Integration | 8 | 2 | bar: W8 to W9
Testing & Validation | 7 | 4 | bar: W7 to W10
Deployment Preparation | 11 | 2 | bar: W11 to W12
Go-Live & Closure | 12 | 1 | bar: W12